## Sheet1
Week | Dates | Theory Topics to cover on Fridays | Assignments and Activities | Deliverables | Evaluated Tasks (from Task Analysis)
#1 | Sep 2 - Sep 6 | (1) Pre-Assessment of the participants (for learner analysis) - CR, VS, KA (2) Information management (collaboration software, statuses, version control) - KA (3) Initial requirements are introduced (may change later) - CR | Participants should learn about other people in their class; what awaits them and how the teams will be selected. | None. Some polls or small exercises are handed in - they help us evaluate the prerequisite knowledge. | None. We assess the prerequisite knowledge of the participants; any gaps and challenges in how they are prepared.
#2 | Sep 9 - Sep 13 | (1) Theory on value propositions | Iteration 0: Setting up a development environment; tools and processes. | Deliverable "Team Working Agreement" - participants define how they want to interact and how they will report their statuses. Deliverable "List of team members", their contacts known across the team (and to us). Deliverable "Value proposition" or "Business case": Team members define their initial idea, why the project is worth doing, the expected outcome and costs (e.g. time estimates) for the whole thing. | (1A) Collaboration tools and practices (2A) Value proposition.
#3 | Sep 16 - Sep 20 | (1) Some stories about the project risks, how to recognize and respond to the risks. CR, VS (2) Automated project builds and continuous integration. |  | Deliverable "Configuration mgmt POC" - show that is possible to build the selected solution using the configuration management approach. Deliverable: Plan for all subsequent iterations. | (4C) Configuration management (3C) Functionality of solution
#4 | Sep 23 - Sep 27 | (1) Automated unit testing. KA (2) Automated project builds and continuous integration. KA | Iteration 1: (Depends on the project). In this iteration participants learn how to interview the stakeholders and clarify the requirements; how to collaborate using the version control. | Deliverable: "Programming technology POC" - Brief report to show that your choice of programming language and framework supports the selected solution for a simple functionality, risks identified early. | (1C) External communication
#5 | Sep 30 - Oct 4 | (1) Automated functional testing. KA (2) How to interact with different stakeholders. VS |  | Functional design document, computer code and other iteration-specific stuff. | (4B) Avoiding fragile, untestable code
#6 | Oct 7 - Oct 11 | (1) Customers, their personas/roles, VS, CR (2) Initial product market fit hypothesis, VS, CR (3) Pains and gains for the customer, VS, CR | Iteration 2: (Depends on the project). In this iteration participants learn how to report statuses, identify teamwork problems such as improper delegation, slackers and or burnouts. |  | (1B) Organizing your teamwork
#7 | Oct 14 - Oct 18 | (4) Organizing your teamworrk: doing work remotely, CR, KA (5) Basics of status reporting - what is achieved, what you plan to do next, what are the blockers or risks. CR, KA (6) How to respond, if project workload is not properly distributed (how to delegate, how to motivate people) CR. KA. |  | Functional design document, computer code and other iteration-specific stuff.
#8 | Oct 21 - Oct 25 | (1) Risk planning and risk management. VS, CR | Iteration 3: (Depends on the project) In this iteration participants learn how to recognize project risks and how to respond to them. They identify changes in the initial plan of iterations (deliverable (3B)).
#9 | Oct 28 - Nov 1 | (1) Software Engineering fundamentals. (2) Iterative methodologies - Agile (Scrum, Kanban, etc.) (3) Principles and advatages of Agile methods. |  | Functional design document, computer code and other iteration-specific stuff.
#10 | Nov 4 - Nov 8 | (1) Issue management, change requests, CR, KA (2) What computer code is reusable. KA | Iteration 4: (Depends on the project) In this iteration participants focus on the standardization and quality of their deliverables, they do all kinds of peer-review and QA - they inspect work created by other team members and fix the mistakes. | Deliverable: English Writing Errata. (Review of existing functional design documents). Deliverable: Code Peer review. Review code of others, create change requests. | (4A) English Writing (4B) Avoid fragile, untestable code
#11 | Nov 11 - Nov 15 | (1) More on automated testing. KA |  | Functional design document, computer code and other iteration-specific stuff. | (3C) Prioritizing functionality, including the features necessary for a "minimum viable product" (MVP)
#12 | Nov 18 - Nov 22 |  | Iteration 5: (Depends on the project) |  | (3C) Prioritizing functionality, including the features necessary for a "minimum viable product" (MVP)
#13 | Nov 25 - Nov 29 | (1) How to package knowledge transfer, how to deploy your solution in the production environment. CR, KA |  | Functional design document, computer code and other iteration-specific stuff. | (3D) Knowledge transfer.
#14 | Dec 2 - Dec 6 | (1) Presenting finished solutions, analyzing feedback from customers, peers, instructors - Part 1. Project teams tell about their achievements. (CR, VS, KA sit back and listen.) | Beta testing and release of the existing solution to the customer. Review of metrics - interactions with the version control (who edited which parts of the files), how informative were the statuses. |  | (3A) Revisit the innovation provided by the solution.
#15 | Dec 9 - Dec 13 | (1) Presenting finished solutions, analyzing feedback from customers, peers, instructors - Part 2. Project teams tell about their achievements. (CR, VS, KA sit back and listen.) |  | Deliverable: "Evaluating the value proposition" - did the solution deliver the value as you planned in the very beginning of your class? Deliverable: Efficiency and Metrics. Reviewing the burndown charts and/or other measures of work efficiency in your team. | (4D) Maintanability of your solution